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TENDER NOTICE
FOR
Strengthening Financing Strategies for Sustainable Development Goals in three states of Himachal Pradesh, Meghalaya and Madhya Pradesh and developing three transformative concept notes for finance mobilisation for SDGs localisation and Climate Action

Background:
In May 2022, Prime Minister Narendra Modi and German Chancellor Olaf Scholz established the Indo-German Partnership for Green and Sustainable Development (GSDP) to expedite the achievement of the UN Sustainable Development Goals (SDGs) and fulfil the commitments of the Paris Climate Agreement. The new collaboration framework emphasises on cooperation through various platforms such as bilateral, trilateral, and multilateral initiatives. The focus is on jointly developing sustainable and inclusive capacity-building projects, addressing climate change, promoting sustainable development, and achieving the Sustainable Development Goals (SDGs). Germany will support the partnership with at least EUR 10 billion of new and additional commitments until 2030.
To gain a better understanding of the precise SDG financing landscape, including existing public resources, funding mechanisms, funding gaps, resource optimisation, the GSDP Support Project seeks to hire the services of a contractor firm. 
Objective:
The assignment aims to:
 (a) analyse the funding gap for SDG Implementation in these three states. (b) analyse the various available methodologies and suggesting a suitable one (backed with reasoning) for SDG budgeting. (c) development of the three concept notes on identified and recommended measures to mobilise finances for from the private sector for achieving any of these SDGs respectively in these three states – Himachal Pradesh (HP), Madhya Pradesh (MP) and Meghalaya (MG).
Tasks of the assignment:
1. Revision of the Stakeholder Mapping and Analysis
2. SDG Funding Gap Analysis: Assessing existing public funding for SDG implementation and identifying disparities between available resources and financial requirements.
3. Identification of Measures to Mobilise Finance: Listing current measures and best practices at various levels to bridge funding gaps.
4. Deep dive into optimal utilisation of the public funds for SDG 3,4,5, and 13
5. Development of Concept Notes: Providing detailed roadmaps for implementing selected financial instruments in the identified three states of HP, MP and MG.
Please refer to the bidding conditions and follow the instructions carefully.

The detailed documentation with regards to this call for proposals includes:
1. The Terms of Reference for the Assignment along with attachment of relevant documents
2. The Assessing Eligibility Grid
3. The Technical Evaluation Grid 
4. Bidding Conditions
5. Financial bid template
6. The General Terms & Conditions of Contracts
Tender timelines:
· [bookmark: _Hlk60495704]Deadline to receive queries: 					12th November 2025
· Clarifications to the queries to be uploaded on web portals: 	17th November 2025
The deadline for submission of proposals: 03rd December 2025
[bookmark: _Hlk64064330]
It is construed that all the terms and conditions of the tender package are acceptable and agreed upon by the participating company. No negotiations/changes to the GTCC shall be acceptable at a later stage.

GIZ reserves the right to cancel/modify this tender and /or reject a bid document including subsequently a technical and financial proposal, without assigning any reasons.
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